## Product Backlog
Product Backlog
Epic ID | Epic Name | User Story ID | User Story Name | Acceptance Citeria | Estimate (User Story Point) | Comment | sprint1 | sprint2 | sprint3 | waterfall
EPIC 1 | Account registration, login and management | US-1-1 | As a customer, | Given the customer has no account on system, | 5 | New Design
|  |  | I want to register an account as a customer, | When the customer creates account,
|  |  | So that I can use the platform as a customer. | Then ensure the account has been created
|  | US-1-2 | As a guide, | Given the guide has no account on system, | 5 | New Design
|  |  | I want to register an account as a guide, | When the guide creates account,
|  |  | So that I can use the platform as a guide. | Then ensure the account has been created
|  | US-1-3 | As a customer, | Given the customer enter email and password, | 3
|  |  | I want to login into the platform, | When the customer login,
|  |  | So that I can find guide and tour program. | Then authenticate the login from that customer.
|  | US-1-4 | As a guide, | Given the guide enter email and password, | 3
|  |  | I want to login into the platform, | When the guide login,
|  |  | So that I can host the tour program. | Then authenticate the login from that customer.
|  | US-1-5 | As a customer, | Given the customer login to system, | 3 | New Design
|  |  | I want to edit my account information, | When the customer edit their profile,
|  |  | So that my information is up to date. | Then ensure edited profile has been recorded.
|  | US-1-6 | As a guide, | Given the guide login to system, | 3 | New Design
|  |  | I want to edit my account information, | When the guide edit their profile,
|  |  | So that my information is up to date. | Then ensure edited profile has been recorded.
EPIC 2 | Guide Matching | US-2-1 | As a guide, | Given the guide login to system, | 13 | Not in requirements, but needed since the program must be create first before customer can join the program.
|  |  | I want to create a tourist program, | When the guide creates the tourist program
|  |  | So that the customer can join the tour program. | Then ensure the program has been created
|  | US-2-2 | As a guide, | Given the guide login to system, | 3 | New Design
|  |  | I want to be notify when customer request to book the program | When the customer request to book the program,
|  |  | So that I can manage their request. | Then notify the guide of customer request.
|  | US-2-3 | As a guide, | Given the guide login to system, | 5 | New Design
|  |  | I want to see customer booking request | When the guide look up their booking request from the customer,
|  |  | So that I view and manage each booking request | Then display all of their the booking request.
|  | US-2-4 | As a guide, | Given the guide recieved customer book request, | 2 | New Design
|  |  | I want to accept the book request of the program from customer, | When the guide accept the customer book request,
|  |  | So that the customer can book the program. | Then accept that customer to book the program.
|  | US-2-5 | As a guide, | Given the guide recieved customer book request, | 2 | New Design
|  |  | I want to reject the book request of the program from customer, | When the guide reject the customer book request,
|  |  | So that the customer can not book the program. | Then reject that customer from booking the program.
EPIC 3 | Program booking | US-3-1 | As a customer, | Given the customer login to system, | 13 | New Design
|  |  | I want to look up for available program by location, | When the customer look up available program by location,
|  |  | So that I can view the available program on that location. | Then display all the available program on that location.
|  | US-3-2 | As a customer, | Given the customer look up the available program, | 5 | New Design
|  |  | I want to view the detail of the selected program, | When the customer view the selected program
|  |  | So that I can see the selected program detail. | Then display detail of the selected program.
|  | US-3-3 | As a customer, | Given the guide has accepted the customer book request, And there are more than 30 minutes before selected program started, | 5 | New Design
|  |  | I want to book the selected program, | When the customer book the selected program,
|  |  | So that I can join the program. | Then redirect customer to payment section.
|  | US-3-4 | As a customer, | Given the customer has join the program, And there are more than 30 minutes before selected program started, | 8
|  |  | I want to cancel my selected program booking, | When the customer cancel the booking for selected program,
|  |  | So that I can get a refund. | Then remove the customer from the program, And refund the customer.
EPIC 4 | Initiating a trip | US-4-1 | As a customer, | Given the customer has requested to join a program, | 3 | New Design
|  |  | I want to receive a notification when the guide acknowledges my trip request, | When the guide accepted the request,
|  |  | So that I can continue to finish the transaction. | Then notify the customer.
|  | US-4-2 | As a customer, | Given the customer has joined the program, | 3
|  |  | I want to get notified about the place, date, and time to meet the guide in advance | When the transaction is complete or it is near the trip date,
|  |  | So that I can properly manage my time and plan. | Then notify the customer.
|  | US-4-3 | As a guide, | Given the customer has joined the program, | 3
|  |  | I want to get notified about the place, date, and time to meet the customer in advance | When the transaction is complete or it is near the trip date,
|  |  | So that I will not forget about my proram plans. | Then notify the guide.
|  | US-4-4 | As a guide, | Given an open trip program has at least 1 customer, | 5
|  |  | I want to be able to close the program reservation any time | When the guide choose to close the reservation,
|  |  | So that I can manage my schedule and workload as I see fit in exchange for losing opportunity to gain more profit. | Then close the reservation and intiate the trip.
EPIC-5 | Make a payment | US-5-1 | As a customer, | Given the guide has accepted the customer request to join the trip, | 3 | New Design -> using coin as payment method in the system and can topup/withdraw coin from banking transfer method
|  |  | I want to be able to see the transaction detail that I have to complete, | When the customer continues to payment section,
|  |  | So that I can complete the transaction using coin in the system. | Then show the customer amount of coin they need to pay with.
|  | US-5-2 | As a customer, | Given the customer proceed to payment section, And the customer has enough coin for the payment, | 8
|  |  | I want to confirm the coin payment to the system, | When the customer confirm payment with their coin in system,
|  |  | So that the coin is sent to system to complete the transaction. | Then deduct the coin from that customer account, and show the payment confirmation. And sent customer book request to the guide of that program.
|  | US-5-3 | As a guide, | Given the customer has completed the payment with coin, | 3
|  |  | I want to be notified when the customer payment is completed and confirmed by system. | When the system has confirmed the payment,
|  |  | So that I can know the customer successfully joined the program. | Then notify the guide.
|  | US-5-4 | As a customer, | Given the customer proceed to coin topup section | 13 | New Design -> using coin as payment method in the system and can topup/withdraw coin from banking transfer method
|  |  | I want to top up coin to the system, | When customer successfully topup amount of X coin from banking method,
|  |  | So that the coin can be use to spent on the platform. | Then add X amount of coin to customer account and show successful prompt.
|  | US-5-5 | As a user, | Given provide correct on payment information, And user has more than 0 coin in their account, | 13 | New Design -> using coin as payment method in the system and can topup/withdraw coin from banking transfer method
|  |  | I want to withdraw coin from the system, | When confirm their withdrawal of X coin,
|  |  | So that there is no remaining coin in the system. | Then deduct the X amount of coin from that user account, And transfer X baht of money to user (from their payment information).

## Sprint3 Backlog
[11 empty] | 14/3 | 15/3 | 16/3 | 17/3 | 18/3 | 19/3 | 20/3 | 21/3 | 22/3 | 23/3 | 24/3 | 25/3 | 26/3 | 27/3 | 28/3 | 29/3 | 30/3 | 31/3 | 2023-01-04 | 2023-02-04 | 2023-03-04
SPRINT | EPIC | EPIC Name | User | User Story | Task | Status | Volunteer |  | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
Sprint 3 | EPIC 2 | Guide Matching | US-2-1 | As a guide, | UI | Done | Bhuribhat | Chanawat |  | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I want to create a tourist program,
So that the customer can join the tour program.
|  |  | US-2-3 | As a guide, | UI | Done | Panithi | Akira |  | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I want to see customer booking request
So that I view and manage each booking request
|  |  | US-2-4 | As a guide, | UI | Done | Pras | Akkharawat |  | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I want to accept the book request of the program from customer,
So that the customer can book the program.
|  |  | US-2-5 | As a guide, | UI | Done | Aunchisa | Teeradon |  | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I want to reject the book request of the program from customer,
So that the customer can not book the program.
| EPIC 3 | Program booking | US-3-4 | As a customer, | Design cancel program booking page | Done | Aunchisa | Teeradon | Todo | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to cancel my selected program booking, | Implement cancel program booking | Done | Pras | Sirapoom | Todo | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  |  |  | So that I can get a refund. | Implement endpoint for cancel program booking | Done | Akira | Panithi | Todo | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 1 | 0
| EPIC 4 | Initiating a trip | US-4-1 | As a customer, | Design notification page (customer) | Done | Aunchisa | Teeradon | Todo | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to receive a notification when the guide acknowledges my trip request, | Implement notification page (customer) | Done | Akkharawat | Sirapoom | Todo | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 1 | 0
|  |  |  | So that I can continue to finish the transaction. | Implement notification fetch (customer) | Done | Pras | Sirapoom |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 2 | 0
[5 empty] | Implement endpoint for notification page (customer) | Done | Teeradon | Bhuribhat |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 1 | 0 | 0
[5 empty] | Implement endpoint to notify when guide acknowledge trip request | Done | Akira | Panithi | Todo | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
|  |  | US-4-2 | As a customer, | Implement endpoint to notify guide meeting place, date and time with guide. | Done | Akira | Akkharawat | Todo | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
|  |  |  | I want to get notified about the place, date, and time to meet the guide in advance |  |  |  |  | Todo
|  |  |  | So that I can properly manage my time and plan. |  |  |  |  | Todo
|  |  | US-4-3 | As a guide, | Design notification page (guide) | Done | Aunchisa | Teeradon | Todo | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to get notified about the place, date, and time to meet the customer in advance | Implement notification page (guide) | Done | Akkharawat | Sirapoom | Todo | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 1 | 0
|  |  |  | So that I will not forget about my program plans. | Implement notification fetch (guide) | Done | Akkharawat | Pras |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 2 | 0
[5 empty] | Implement endpoint for notification page (guide) | Done | Teeradon | Chanawat |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 1 | 1 | 0
[5 empty] | Implement endpoint to notify meeting place, date and time with customer | Done | Bhuribhat | Chanawat | Todo | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
| EPIC 5 | Make a payment | US-5-1 | As a customer, | Design transaction detail page | Done | Aunchisa | Teeradon | Todo | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to be able to see the transaction detail that I have to complete, | Implement transaction detail page | Done | Bhuribhat | Chanawat | Todo | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 0 | 0
|  |  |  | So that I can complete the transaction using coin in the system. | Implement endpoint for transaction detail page | Done | Bhuribhat | Chanawat |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
|  |  | US-5-2 | As a customer, | Design transaction confirm page | Done | Aunchisa | Teeradon | Todo | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to confirm the coin payment to the system, | Implement transaciton confirm page | Done | Akkharawat | Aunchisa | Todo | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  |  |  | So that the coin is sent to system to complete the transaction. | Implement endpoint for transaction confirm page | Done | Bhuribhat | Chanawat | Todo | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  |  | US-5-3 | As a guide, | Implement endpoint to notify guide when customer completes their transaction | Done | Akkharawat | Panithi | Todo | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  |  |  | I want to be notified when the customer payment is completed and confirmed by system. |  |  |  |  | Todo
|  |  |  | So that I can know the customer successfully joined the program. |  |  |  |  | Todo
|  |  | US-5-4 | As a customer, | Design coin topup page | Done | Aunchisa | Teeradon |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to top up coin to the system, | Implement coin topup page | Done | Pras | Sirapoom |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 0
|  |  |  | So that the coin can be use to spent on the platform. | Implement endpoint for coin topup page | Done | Akira | Panithi |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 5 | 5 | 3 | 1 | 0
|  |  | US-5-5 | As a user, | Design coin withdraw page | Done | Aunchisa | Teeradon |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to withdraw coin from the system, | Implement coin withdraw page | Done | Pras | Sirapoom |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 2 | 0
|  |  |  | So that there is no remaining coin in the system. | Implement endpoint for coin withdraw page | Done | Akira | Panithi |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 4 | 4 | 2 | 2 | 0
Total | [9 empty] | 107 | 100 | 99 | 97 | 93 | 92 | 91 | 91 | 89 | 89 | 85 | 85 | 82 | 82 | 80 | 71 | 71 | 63 | 60 | 39 | 23 | 0
Sprint Goal
Implement make payment and integrate the system
[8 empty] | Name |  | Sum hour
[8 empty] | Akira |  | 13
[8 empty] | Teeradon |  | 12
[8 empty] | Panithi |  | 13
[8 empty] | Bhuribhat |  | 10.5
[8 empty] | Chanawat |  | 10.5
[8 empty] | Pras |  | 13
[8 empty] | Siripoom |  | 13.5
[8 empty] | Akkharawat |  | 11.5
[8 empty] | Aunchisa |  | 10

## Sprint2 Backlog
[11 empty] | 16/2 | 17/2 | 18/2 | 19/2 | 20/2 | 21/2 | 22/2 | 23/2 | 24/2 | 25/2 | 26/2 | 27/2 | 28/2 | 2023-01-03 | 2023-02-03 | 2023-03-03 | 2023-04-03 | 2023-05-03 | 2023-06-03 | 2023-07-03 | 2023-08-03 | 2023-09-03 | 2023-10-03 | 2023-11-03 | 2023-12-03 | 13/3
SPRINT | EPIC | EPIC Name | User | User Story | Task | Status | Volunteer |  | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26
Sprint 2 | EPIC 1 | Account registration, login and management | US-1-1 | As a customer, | UI | Done | Akira | Teeradon | Todo | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to register an account as a customer, |  |  |  |  | Todo
|  |  |  | So that I can use the platform as a customer. |  |  |  |  | Todo
|  |  | US-1-2 | As a guide, | UI | Done | Akira | Teeradon | Todo | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to register an account as a guide, |  |  |  |  | Todo
|  |  |  | So that I can use the platform as a guide. |  |  |  |  | Todo
|  |  | US-1-3 | As a customer, | Design login page (Customer) | Done | Aunchisa | Teeradon |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to login into the platform, | Implement customer login | Done | Pras | Sirapoom |  | 8 | 8 | 6 | 6 | 5 | 5 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | So that I can find guide and tour program. | Implement endpoint for customer login | Done | Akira | Panithi |  | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US-1-4 | As a guide, | Design login page (Guide) | Done | Aunchisa | Teeradon |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to login into the platform, | Implement guide login | Done | Akkharawat | Sirapoom |  | 8 | 8 | 8 | 6 | 6 | 6 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | So that I can host the tour program. | Implement endpoint for guide login | Done | Akira | Panithi |  | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US-1-5 | As a customer, | UI | Done | Aunchisa | Bhuribhat | Todo | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to edit my account information, |  |  |  |  | Todo
|  |  |  | So that my information is up to date. |  |  |  |  | Todo
|  |  | US-1-6 | As a guide, | UI | Done | Aunchisa | Bhuribhat | Todo | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to edit my account information, |  |  |  |  | Todo
|  |  |  | So that my information is up to date. |  |  |  |  | Todo
| EPIC 2 | Guide matching | US-2-1 | As a guide, | UI | Stlying | Aunchisa | Teeradon | Todo | 5 | 17 | 17 | 17 | 17 | 15 | 15 | 15 | 15 | 13 | 13 | 13 | 12 | 12 | 12 | 10 | 10 | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 6 | 3
|  |  |  | I want to create a tourist program, |  |  |  |  | Todo
|  |  |  | So that the customer can join the tour program. |  |  |  |  | Todo
|  |  | US-2-3 | As a guide, | UI | Stlying | Panithi | Chanawat | Todo | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  |  |  | I want to see customer booking request |  |  |  |  | Todo
|  |  |  | So that I view and manage each booking request |  |  |  |  | Todo
|  |  | US-2-4 | As a guide, | UI | Stlying | Chanawat | Teeradon | Todo | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  |  |  | I want to accept the book request of the program from customer, |  |  |  |  | Todo
|  |  |  | So that the customer can book the program. |  |  |  |  | Todo
|  |  | US-2-5 | As a guide, | UI | Stlying | Chanawat | Panithi | Todo | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  |  |  | I want to reject the book request of the program from customer, |  |  |  |  | Todo
|  |  |  | So that the customer can not book the program. |  |  |  |  | Todo
| EPIC 3 | Program booking | US-3-1 | As a customer, | Design lookup available program page | Done | Aunchisa | Teeradon | Todo | 3 | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to look up for available program by location, | Implement available program lookup | Done | Pras | Sirapoom | Todo | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 5 | 5 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  |  |  | So that I can view the available program on that location. | Implement endpoint for available program lookup | Done | Bhuribhat | Chanawat |  | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement endpoint to get available program | Done | Bhuribhat | Chanawat | Todo | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US-3-2 | As a customer, | Design lookup selected program page | Done | Aunchisa | Teeradon | Todo | 3 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to view the detail of the selected program, | Implement selected program lookup | Done | Akkharawat | Pras | Todo | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0
|  |  |  | So that I can see the selected program detail. | Implement endpoint for selected program lookup | Done | Akira | Panithi | Todo | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement endpoint to get selected program | Done | Akira | Panithi |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US-3-3 | As a customer, | Implement book request | Done | Akkharawat | Aunchisa | Todo | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  |  |  | I want to book the selected program, | Implement endpoint for requesting to book the available program | Done | Bhuribhat | Chanawat | Todo | 5 | 5 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | So that I can join the program. | Implement endpoint for redirecting to payment page | Done | Bhuribhat | Teeradon | Todo | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | [9 empty] | 106 | 114 | 110 | 107 | 103 | 91 | 75 | 69 | 62 | 54 | 54 | 54 | 52 | 45 | 34 | 30 | 27 | 26 | 24 | 24 | 24 | 24 | 24 | 24 | 23 | 21 | 9
Sprint Goal
Implement guide matching and program booking
[8 empty] | Name |  | Sum hour
[8 empty] | Akira |  | 11
[8 empty] | Teeradon |  | 13
[8 empty] | Panithi |  | 11
[8 empty] | Bhuribhat |  | 12
[8 empty] | Chanawat |  | 11.5
[8 empty] | Pras |  | 12
[8 empty] | Siripoom |  | 12
[8 empty] | Akkharawat |  | 10.5
[8 empty] | Aunchisa |  | 13

## Sprint1 Backlog
[11 empty] | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| EPIC | EPIC Name | User | User Story | Task | Status | Volunteer |  | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
Sprint 1 | EPIC 1 | Account registration, login and management | US-1-1 | As a customer, | Setup backend server & architecture | Done | Panithi | Akira | Todo | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to register an account as a customer, | Setup database (MongoDB) | Done | Panithi | Akira | Todo | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | So that I can use the platform as a customer. | Setup React, folder structures, .gitignore, prettier, and NextJS | Done | Pras | Panithi | Todo | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Setup MUI and design system | Done | Pras | Panithi | Todo | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Design customer register page | Done | Aunchisa | Akira | Todo | 3 | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Design model schema | Done | Teeradon | Chanawat | Todo | 5 | 5 | 4 | 4 | 4 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement customer | Done | Teeradon | Chanawat | Todo | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement register as customer page | Done | Chanawat | Bhuribhat | Todo | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
[5 empty] | Implement endpoint for creating a customer user account | Done | Chanawat | Bhuribhat | Todo | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement landing page and Nav bar | Done | Sirapoom | Aunchisa | Todo | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 0
|  |  | US-1-2 | As a guide, | Design guide register page | Done | Aunchisa | Akira | Todo | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to register an account as a guide, | Implement guide | Done | Akkharawat | Teeradon | Todo | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | So that I can use the platform as a guide. | Implement register as guide page | Done | Akkharawat | Teeradon | Todo | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0
[5 empty] | Implement endpoint for creating a guide user account | Done | Akkharawat | Teeradon | Todo | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US-1-5 | As a customer, | Design customer account page (including profile and edit button) | Done | Aunchisa | Akira | Todo | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to edit my account information, | Implement view and edit customer account info page | Done | Teeradon | Sirapoom | Todo | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
|  |  |  | So that my information is up to date. | Implement endpoint for updating customer acount information | Done | Teeradon | Sirapoom | Todo | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US-1-6 | As a guide, | Design guide account page (including profile and edit button) | Done | Aunchisa | Akira | Todo | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to edit my account information, | Implement view and edit guide account info page | Done | Panithi | Pras | Todo | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0
|  |  |  | So that my information is up to date. | Implement endpoint for updating guide acount information | Done | Panithi | Pras | Todo | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EPIC 2 | Guide Matching | US-2-1 | As a guide, | Design create program page | Done | Aunchisa | Akira | Todo | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to create a tourist program, | Implement create program page for tourist | Done | Bhuribhat | Akkharawat | Todo | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0
|  |  |  | So that the customer can join the tour program. | Implement endpoint for creating program | Done | Bhuribhat | Akkharawat | Todo | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US-2-3 | As a guide, | Design booking request page | Done | Aunchisa | Akira | Todo | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | implement dashboard page to view all created program | Done | Bhuribhat | Sirapoom | Todo | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 0
|  |  |  | I want to see customer booking request | Implement view and edit program page | Done | Chanawat | Sirapoom | Todo | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 3 | 3 | 3 | 2 | 2 | 0
|  |  |  | So that I view and manage each booking request | implement endpoints for get programs and edit program | Done | Chanawat | Sirapoom | Todo | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US-2-4 | As a guide, | Design guide acceptance page | Done | Aunchisa | Akira | Todo | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to accept the book request of the program from customer, | Implement component to view requests from customer | Done | Pras | Akkharawat | Todo | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0
|  |  |  | So that the customer can book the program. | implement endpoint for accepting request | Done | Pras | Akkharawat | Todo | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement accept-request | Done | Pras | Akkharawat | Todo | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US-2-5 | As a guide, | Design guide rejection history page | Done | Aunchisa | Akira | Todo | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I want to reject the book request of the program from customer, | implement reject-request | Done | Panithi | Bhuribhat | Todo | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 1 | 0 | 0 | 0
|  |  |  | So that the customer can not book the program. | implement endpoint for rejecting request | Done | Panithi | Bhuribhat | Todo | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | [6 empty] | 116 | 114 | 113 | 112 | 110 | 108 | 107 | 103 | 89 | 87 | 80 | 60 | 56 | 49 | 43 | 39 | 24 | 24 | 22 | 17 | 10 | 0
Sprint Goal
Implement registration and account management system and system for guide user
sum hour
[5 empty] | Akira |  | 15
[5 empty] | Teeradon |  | 11.5
[5 empty] | Panithi |  | 13
[5 empty] | Bhuribhat |  | 13.5
[5 empty] | Chanawat |  | 12
[5 empty] | Pras |  | 11.5
[5 empty] | Siripoom |  | 12.5
[5 empty] | Akkharawat |  | 13
[5 empty] | Aunchisa |  | 14